## Project Management Questions
Projekt: |  |  |  | Imię i nazwisko:
Data: |  |  |  | Stanowisko:
Kwestionariusz Podejścia do Projektu AgilePM |  | Wskazać najbliższa zbiorową opinię |  |  |  |  | We właściwych miejscach wypowiedzieć się na temat problemów lub ryzyk związanych z bardziej negatywną reakcją na ten aspekt metody AgilePM
ID | Stwierdzenie | Zgadzam się w 100% | Zgadzam się | Neutral | Nie zgadzam się | Stanowczo nie zgadzam się
1 | Cel biznesowy projektu został jasno określony i widzą go wszyscy członkowie zespołu projektowego
2 | Widać wyraźnie, że właścicielami projektu są Sponsor Biznesowy i/lub Wizjoner Biznesu
3 | Wszyscy: Sponsor Biznesowy, Wizjoner Biznesu i Koordynator Techniczny rozumieją i akceptują filozofię AgilePM
4 | Istnieje jasno określony zakres czasowy projektu
5 | Istnieje możliwość określania priorytetów wymogów, można przyjąć bez problemu, że nie wszystkie wymogi są wymogami "Must Have"
6 | Wymogi zostały określone na wysokim poziomie na początku projektu i wszyscy rozumieją, że w trakcie jego realizacji mogą wystąpić zmiany
7 | Akceptuje się, że szczegóły wymogów i rozwiązanie wyłonią się w trakcie realizacji projektu
8 | Sponsor Biznesowy i Wizjoner Biznesu są świadomi znaczenia aktywnego zaangażowania biznesu i mają chęci oraz władzę, by zaangażować w projekt odpowiednie zasoby biznesowe
9 | Ambasadorzy Biznesu mają wystarczające kompetencje i uprawnienia, by kierować bieżącą ewolucją rozwiązania
10 | Twórcy Rozwiązania mają wystarczające upoważnienia i kompetencje, by zapewnić najlepsze możliwe rozwiązanie z perspektywy biznesowej z wcześniej ustalonymi ograniczeniami architektonicznymi
11 | Zasoby realizacji rozwiązania zostały przydzielone na odpowiednim poziomie, a skład zespołu pozostanie generalnie stały w trakcie realizacji projektu (lub przynajmniej w trakcie każdej zmiany)
12 | Zespół Projektowy i Zespół Rozwoju Rozwiązania potrafią dostosować role i zadania w ramach AgilePM
13 | Twórcy Rozwiązań będą mogli mieć łatwy dostęp do Ambasadorów Biznesu i Doradców Biznesowych w trakcie projektu
14 | Zespół Rozwoju Rozwiązania (w tym zarówno zasoby rozwoju biznesu jak i opracowania rozwiązań) będą posiadały odpowiednią zbiorczą wiedzę i/lub kwalifikacje merytoryczne niezbędne do opracowania rozwiązania
15 | Zespół Rozwoju Rozwiązania (w tym zarówno zasoby biznesowe jak i zasoby budowy rozwiązania) będą posiadały odpowiednie umiejętności miękkie (komunikacja, negocjacje, itp.) niezbędnie do skutecznej współpracy między sobą i z innymi wokół
16 | Strategie stałej komunikacji i wspólnej pracy wystarczą do wyraźnego wspierania interacyjnego opracowania rozwiązania
17 | Narzędzia do budowy rozwiązania i technologia rozwiązania wspierają interacyje podejście budowy rozwiązania
18 | Brak ograniczeń technicznych, ograniczeń wynikających z umowy lub innych ograniczeń uniemożliwiających podzielenie rozwiązania na części w celu jego realizacji i ukończenia (nawet jeżeli produkty takich części nie zostaną od razu wykorzystane)
19 | Wszyscy uczestnicy projektu rozumieją i akceptują, ze terminowa dostawa możliwego do przyjęcia rozwiązania stanowi zasadniczą miarę powodzenia projektu
20 | Wszystkie strony zgadzają się, że zasadnicze znaczenie ma ciągła ocena przydatności wszystkich produktów projektu w trakcie ich opracowywania
21 | Brak obowiązujących norm, standardów lub praktyk, które byłyby wbrew opracowaniu rozwiązania od wyjściowego zestawu wymagań wyższego poziomu
Ogólne uwagi na temat przydatności lub ryzyka związanego z podejściem AgilePM:
© 2013 Dynamic Systems Development Method Limited
Note on H5: Clarity of business driver will help maintain a real focus on delivering the solution with the optimum business benefit within the constraints of time and resources agreed
Note on H6: Attendance at workshops, willingness to work on definition of project objective
Note on H7: Whole team including Business Managers and users may need training
Note on H8: It focuses people's belief in timeboxes if development timeframe is fixed and/or significantly constrained
Note on H9: It allows for project to be kept on-time if no more than 60% of estimated effort is allocated to 'Must Have' requirements
Note on H10: It is helpful if requirements are only understood at a high level at the outset of the project , and/or are likely to change during development
Note on H11: Specifically, there will not be anything created up-front that is in anyway akin to a functional or design specification. The level of detail normally associated with these documents must be allowed to evolve over time
Note on H12: The active and continual involvement of business representatives is absolutely critical to the success of a DSDM Atern project. It does not have to be full time or even every day but it must be sufficient to provide all other members of the team with what they need to develop a solution that is truly fit for business purpose on the day of delivery
Note on H13: The vast majority of decisions made by the Business Ambassadors must stick. The team will not be able to maintain their commitment to an on-time to budget delivery if there is too much rework associated with over-turned decisions
Note on H14: There is no time allowed for constant validation of detailed technical decisions. Just as Business Ambassadors must be empowered to guide the detail of the development, the developers must be empowered to develop it in the best way available to them.
Note on H15: Stability of the team allows for faster progress and reduces the need for documentation
Note on H16: It is vital that all the responsibilities described in the full set of DSDM Atern roles are covered by somebody in the team. Failings in this area will result in potentially critical aspects of quality being missed
Note on H17: Co-location of business representatives with the rest of the team is ideal but where this is not feasible time, facilities and mechanisms for frequent ad-hoc communication between all parties must be available.
Note on H18: Where this is not universally feasible, it is vital that the effort attributed to Must Have requirements is reduced sufficiently to allow for on-the-job development of such knowledge and experience.
Note on H19: Like all the Agile approaches DSDM Atern relies heavily on verbal communication skills. The team as a whole must be ready, willing AND ABLE to reach rapid consensus on the detail of the work that needs to be done.
Note on H20: There is no place in a DSDM Atern project for strict demarcation of responsibilities. Where such restrictive working practices exist either physically or culturally within an organisation an approved strategy for dealing with this should be in place before development starts
Note on H21: Short cycle times in the Identify-Plan-Evolve-Review process are important. The technology used in development of the solution should allow this cycle to complete in the time frame of minutes and hours rather than days or weeks.
Note on H22: The solution should be developed in short, focussed, well controlled periods of activity (measured in weeks rather than months) that result in a potentially deployable subset of the solution.
Note on H23: This is primarily a matter of focus and pragmatism to ensure maximum business benefit for minimum development effort. It is important to realise that early delivery of a 'just sufficient' makes more business sense than later delivery of a solution with 'all the bells and whistles'
Note on H24: It is important that all aspects of the solution are continually reviewed in order to reveal deficiencies of whatever cause or nature. There is limited value associated with delivering a solution on time and within budget if agreed levels of quality are compromised
Note on H25: Mandatory standards requiring, for example, a detailed up-front specification to be created, or practices limiting the involvement of the 'customer' of the project will significantly reduce the benefits associated with the DSDM Atern approach