## Sheet1
AgilePM® V1 Project Health Check Questionnaire (PHCQ) v1.1 (11.2014) by Miroslaw Dabrowski www.miroslawdabrowski.com
Project: |  | Author:
Date: |  | Position: | AgilePM® V2 inteactive mind map | AgilePM® V2 Exam Simulator
ID | Question | Answer
1 | Business sponsorship and expectations
2 | Is there a stable, ongoing funding for the whole project and AgilePM approach?
3 | What is the status of senior management involvement, commitment and satisfaction?
4 | Is the project progress visible through frequent deliverables?
5 | How satisfied is the business with project progress so far?
6 | How well are business expectations being managed?
7 | How well Business Ambassador (BAMB) defines his / her low level requirements?
8 | Is business feedback after Timebox review incorporated to the project?
9 | Does project has clearly defined, communicated and understood by every project member Business Case and Project Vision?
10 | Business involvement
11 | How is business involvement being achieved?
12 | Does Business Visionary (BV) is engaged during Timebox Kick-Off and Close-Out sessions?
13 | Does Business Ambassador (BAMB) within SDTs is continual, active and ongoing (collaboration)?
14 | Does project involves Business Advisors (BADV) and their involvement continual, active and ongoing (collaboration)?
15 | Do we have all the right business representatives (empowered, decisive, available, with business know-how)?
16 | Does business involvement is visible during Timeboxes?
17 | Does Business Ambassador (BAMB) is always present on Daily Stand-ups sessions?
18 | Are Business Visionary (BV) and Technical Coordinator (TC) actively engaged in the Timebox iterations (investigate, refine, consolidate)?
19 | Roles and responsibilities
20 | Are all AgilePM roles allocated to the project team (excluding DC, WF, BADV, TADV)?
21 | Are there any roles combined? Are there any conflicts of interests between them?
22 | Do all project members members carry out their responsibilities?
23 | Do all SDTs member are open to cross boundaries (excluding BAMB) associated with roles when project health requires this?
24 | Empowerment
25 | Are the business representatives empowered (BS, BV, BAMB, BADV)?
26 | Is the team self-directed, self-organising, self-managed?
27 | How does escalation work?
28 | How often Business Ambassador (BAMB) escalate issues? Is he a 'true' Business Ambassador?
29 | How often escalation is used (escalation outside SDTs)?
30 | Team structure
31 | What is the project team structure?
32 | What is the size of the SDT(s)?
33 | Do the SDT(s) have the right tools to accompilish Timebox/Increment?
34 | Do the SDT(s) have the right skills to accompilish Timebox/Increment?
35 | Do the SDT(s) have the authonomy?
36 | Is there any sourcing (outsourcing / insourcing etc.)?
37 | Are the SDT(s) collocated? If not, how is virtual team collocation achieved?
38 | How SDT(s) is communicating with Business Ambassador (BAMB)?
39 | Is the physical environments suitable?
40 | Are team members fully dedicated (time allocation) to the project?
41 | Team dynamics
42 | Are the team goals clearly defined and understood by all team members and relevand business representatives (BV, BAMB)?
43 | How well does the team work together?
44 | Do the team(s) accepts their Team Leader (TL)?
45 | Does Team Leader (TL) acts as a servant-leader?
46 | How is team morale, motivation, enthusiasm, commitment?
47 | What is the turnover?
48 | Does the SDTs organises itself and meets during Daily Stand-ups even when Team Leader (TL) is absent?
49 | Training
50 | How all project member received AgilePM training (awareness level / theory)?
51 | How all project member received AgilePM workshop (pragmatic level / practice)?
52 | Do all project members buy in to the AgilePM Philosophy, approach and style of working?
53 | Is there effective mentoring on the project by DSDM Coach (DC)?
54 | Facilitated Workshops
55 | Are facilitated workshops used?
56 | Does business representatives are actively engaged during the facilitated workshops?
57 | How effective are facilitated workshops?
58 | Is there a clearly defined Workshop Facilitator (WF) role?
59 | Is Workshop Facilitatior (WF) truly indemendent to the workshop output / outcome?
60 | How many facilitated workshops were held during Feasibility and Foundations phases?
61 | Prioritisation
62 | Is MoSCoW prioritisation is used across the whole projects (all Increments and Timeboxes)?
63 | Are MoSCoW priorities being adhere to?
64 | Are Must Have requirements really represents Must Haves and without them solution does not provide any value?
65 | Does everyone buy in to the MoSCoW priorities (especially business representatives: BS, BV, BAMB, BADV)?
66 | How much reprioritization has been done and how?
67 | Does reprioritization occurs during / inside the Timebox PRL?
68 | Timeboxing
69 | Are Timeboxes ar right level of granulity?
70 | Are Timeboxes being respected (fixed time)?
71 | Do Timeboxes have a good mix of use must, should and could for requirements?
72 | Do Timeboxes have a good mix of use must, should and could for tests?
73 | How many features are being passed between Timeboxes and of what priority?
74 | How it the end of Timebox process working?
75 | Iterative development
76 | Is iterative development taking place effectively?
77 | Are the iterative controls being followed (e.g. reviews and retrospective sessions)?
78 | Are the Timebox iterations (Investigate, Refine, Consolidate) being followed?
79 | Incremental delivery
80 | Is the project value delivered through multiple (2+) deployments?
81 | Products
82 | Have the AgilePM products been created from templates (based on experience and review form previous projects)?
83 | Have the AgilePM products been tailored?
84 | Is product quality satisfactory to the business / governance requirements?
85 | Do the products meet their AgilePM quality criteria?
86 | Are responsibilities related to products are clearly and unambiguously defined, understood, agreed and accepted?
87 | Have non-functional requirements (NFR) been considered?
88 | Is appropriate documentation produced, used, maintained, reviewed, archived and disposed (a.k.a. products lifecycle)?
89 | Does project requires every product created so far?
90 | Does each created product provided value (is there a need for creating this product once again)?
91 | Reviews
92 | How is the Evolving Solution reviewed?
93 | Are comments from reviews being incorporated into the Evolving Solution or team working practices?
94 | How are reviews recorded?
95 | How are deliverables accepted?
96 | Technical
97 | Is the development environment appropriate for AgilePM?
98 | Is the techical infrastructure in place and/or familar to the SDT(s)?
99 | Are technical standards defined understood, agreed, accepted and followed by SDT(s)?
100 | Does Team Leader (TL) have clear guidance on how to implement technical standards from Technical Coordinator (TC)?
101 | Does technical acrchitecture is clearly defined and communicated to all project members?
102 | Lifecycle
103 | Is the lifecycle being followed?
104 | Has the lifecycle beed tailored?
105 | Is the Project Approach Questionnaire (PAQ) used effectively?
106 | Is the Project Approach Questionnaire (PAQ) template updated since last use to incorporate lessons learnt?
107 | Project management
108 | Is the project management style appropriate to AgilePM?
109 | How is the project's governing body working?
110 | Planning and estimation
111 | Are AgilePM planning deliverables produced (Outline Plan, Delivery Plan, Deployment Plan)?
112 | Does SDT(s) track their work progress?
113 | Does SDT(s) estimate their work?
114 | Does Timebox estimation work and is used as a basis for project planning?
115 | Does Timebox estimation is done by SDT(s) without business interruption?
116 | Are estimates realistic?
117 | How are estimates done?
118 | Is team(s) velocity is tracked and used for further estimation?
119 | Is the project resourced as planned?
120 | How many changes are occurring in terms of project resourcing during Timeboxes?
121 | Change management
122 | Is there a change control process? Is it followed?
123 | Is the change control process too bureaucratic?
124 | Are reprioritisations fed into the change control processes?
125 | Configuration management
126 | Are evolving products regularly baselined?
127 | Is there a configuration management process? Is it followed?
128 | Is backtracking (tracing) done where necessary?
129 | Risk and issues
130 | Have risks and issues specific to AgilePM been identified?
131 | Are risk is being managed proactively through Timeboxes?
132 | Are risk topic is raised during Kick-Off meetings?
133 | Are risks being managed?
134 | Are issues being managed?
135 | Testing
136 | Is there a Testing Strategy?
137 | Is Testing Strategy under governance of Technical Coordinator (TC)?
138 | Does each SDT has at least one Solution Tester (ST)?
139 | Does Solution Tester (ST) conducts solution tests during Timebox?
140 | Does testing involves risk based testing approach?
141 | Does testing involves prioritised testing based on MoSCoW prioritisation?
142 | Who is involved in testing?
143 | Are the AgilePM concepts for testing being applied?
144 | End of increment
145 | Have all requirements ommited in the increment been identified?
146 | Is there sufficiant information to decide to proceed with further development?
147 | Have all lessons learned beed documented?
148 | Deployment
149 | Does communication between SDT(s) and deployment team is effective?
mindmeister.com/401654536
miroslawdabrowski.com