## AgilePM V2 - PHCQ
AgilePM® V2 Project Health Check Questionnaire (PHCQ) v1.1 (06.2014) by Miroslaw Dabrowski www.miroslawdabrowski.com
Project | Test Project ACME | Author | Mirosław Dąbrowski
Date | 2015-05-01 | Position | Agile/DSDM Coach |  | AgilePM® V2 inteactive mind map | AgilePM® V2 Exam Simulator
Scoring: 0 - Never, 1 - Rarely 2 - Occasionally, 3 - Often, 4 - Very Often, 5 - Always
ID | Section / Question | Score | % | Comments
Business sponsorship and expectations
1 | There is stable, ongoing funding for the whole project and DSDM approach | 1
2 | Senior management is involved, committed and satisfied with the project so far | 1
3 | The project progress is visible outside through frequent deliverables | 2
4 | Business (Business Ambassador (BAMB) and Business Sponsor (BS)) is satisfied with project progress so far | 2
5 | Business expectations are being managed well | 3
6 | Business Ambassador (BAMB) can clearly define and communicated his / her low level requirements | 4
7 | Project has clearly defined, communicated and understood by every project member Business Case and Project Vision | 5
section score |  | 18 | 51.43%
Business involvement and emgagement
8 | Business involvement is achieved throught the whole lifespan of the project | 1
9 | Business Visionary (BV) is engaged during Timebox Kick-Off and Close-Out sessions | 1
10 | Business Ambassador (BAMB) involvement within SDTs is continual, active and ongoing (proactive collaboration) | 2
11 | Project involves Business Advisors (BADV) and their involvement is continual, active and ongoing (proactive collaboration) | 1
12 | All business representatives have the right characteristics (empowered, decisive, available, with business know-how) | 1
13 | Business involvement is visible during Timeboxes | 3
14 | Business Ambassador (BAMB) is always present on Daily Stand-ups sessions | 1
15 | Business Visionary (BV) and Technical Coordinator (TC) are actively engaged in the Timebox iterations | 1
16 | Business feedback after Timebox review is incorporated to the project | 5
17 | Business Visionary (BV) is engaged in session / meeting dedicated for claryfing PRL items (a.k.a. PRL refinement) | 4
section score |  | 20 | 40%
Roles and responsibilities
18 | All DSDM roles allocated to the project team (excluding DC, WF, BADV, TADV) | 4
19 | If roles are combined there are no conflicts of interests between them | 5
20 | There is no problems with availability of people who have multiple roles | 5
21 | All project members members carry out their responsibilities | 4
22 | All SDTs member are open to cross boundaries (excluding BAMB) associated with roles when project health requires this | 3
section score |  | 21 | 84%
Empowerment
23 | The business representatives are empowered (BS, BV, BAMB, BADV) | 4
24 | The SDTs are self-directed, self-organising and self-managed | 5
25 | Escalation work very well with clear path to whom we should escalate | 2
26 | Business Ambassador (BAMB) very rarely escalate issues (he is a 'true' Business Ambassador) | 5
27 | Escalation is used very rarely if none (escalation outside SDT(s)) | 5
section score |  | 21 | 84%
Team structure
28 | Project team structure is clear and understood by all stakeholders | 5
29 | Size of the SDT(s) is in appropriate levels | 2
30 | SDT(s) have the right tools to accompilish Timebox / Increment | 4
31 | SDT(s) have the right skills to accompilish Timebox / Increment | 2
32 | SDT(s) have the authonomy | 2
33 | There sourcing model work very well (outsourcing / insourcing etc.) | 5
34 | SDT(s) are collocated (If not, virtual team communication and collaboration works very well) | 1
35 | SDT(s) is communicating often with Business Ambassador (BAMB) | 4
36 | Physical environments are suitable for work | 2
37 | Team members are fully dedicated (time allocation) to the project | 4
section score |  | 31 | 62%
Team dynamics
38 | Team goals are clearly defined and understood by all team members and relevand business representatives (BV, BAMB) | 5
39 | The team work well together | 4
40 | People are open and eager for helping others even if this requires working outside their responsibilities scope (using tacit knowledge) | 4
41 | If needed people are open and eager for learning other's needs (continuous integration) | 4
42 | SDT(s) accepts their Team Leader (TL) | 5
43 | Team Leader (TL) acts as a servant-leader | 3
44 | Team morale, motivation, enthusiasm, commitment are very good | 5
45 | Turnover in SDT(s) is very low if none | 5
46 | SDTs organises itself and meets during Daily Stand-ups even when Team Leader (TL) is absent | 5
section score |  | 40 | 88.89%
Training
47 | All project members received DSDM training (awareness level / theory) | 2
48 | All project members received DSDM workshop (pragmatic level / practice) | 2
49 | All project members buy in to the DSDM Philosophy, Approach and style of working | 2
50 | There is effective mentoring for the project team member by DSDM Coach (DC) | 2
51 | There is effective mentoring for the business representatives (BS, BV, BA and end client representatives) on the project by DSDM Coach (DC) | 2
section score |  | 10 | 40%
Facilitated Workshops
52 | Facilitated workshops are used often during the project | 2
53 | Business representatives are actively engaged during the facilitated workshops | 2
54 | Facilitated workshops are effective | 2
55 | There is a clearly defined Workshop Facilitator (WF) role | 2
56 | Workshop Facilitatior (WF) is truly indemendent to the workshop output / outcome | 2
57 | There are at least one facilitated workshop held during Feasibility and Foundations phases | 2
section score |  | 12 | 40%
Prioritisation
58 | MoSCoW prioritisation is used across the whole projects (all Increments and Timeboxes) | 1
59 | MoSCoW priorities are being adhere to | 1
60 | Must Have requirements really represents Must Haves and without them solution does not provide any value (MVP) | 2
61 | Everyone buy in to the MoSCoW priorities (especially business representatives: BS, BV, BAMB, BADV) | 2
62 | Reprioritization is often and is always done together with business representatives (BS, BA) | 1
63 | Reprioritization does NOT occur during / inside the Timebox PRL | 2
section score |  | 9 | 30%
Timeboxing
64 | Timeboxes are at right level of granulity | 2
65 | Timeboxes are respected (fixed time) | 5
66 | Timeboxes have a good mix of use must, should and could for requirements | 3
67 | Timeboxes have a good mix of use must, should and could for tests | 2
68 | Only few features are being passed between Timeboxes (and they have low priority; Should or Could) | 3
69 | End of Timebox process is working efficiently | 1
section score |  | 16 | 53.33%
Iterative development
70 | Iterative development is taking place effectively | 3
71 | Iterative controls are being followed (e.g. reviews and retrospective sessions) | 4
72 | Epics are constantly developed using iterative development cycle (including customer feedback loops) | 1
73 | Uset Stories are refined using iterative development up to Tasks level | 1
74 | Timebox iterations (Conversation, Thought, Action, Conversation) are being followed | 2
section score |  | 11 | 44%
Incremental delivery
75 | Project value delivered through multiple (2+) deployments | 3
76 | Delivered features represents at least all required Must haves from MoSCoW priortities | 2
77 | All bugs from previous increment (not Timebox) are fixed in the next one | 2
section score |  | 7 | 46.67%
Products
78 | DSDM products have been created from templates (based on experience and review form previous projects) | 3
79 | DSDM products have been tailored | 2
80 | Products quality is satisfactory to the business / governance requirements | 5
81 | Products meet their DSDM quality criteria | 2
82 | Responsibilities related to products are clearly and unambiguously defined, understood, agreed and accepted | 4
83 | Non-functional requirements (NFR) have been considered | 1
84 | Appropriate documentation is produced, used, maintained, reviewed, archived and disposed (a.k.a. products lifecycle) | 2
85 | Project uses minimal set of products | 2
86 | Each created product delivers value (Is there a need for creating this product once again? Is there a reciver reading and giving feedback?) | 3
section score |  | 24 | 53.33%
Reviews
87 | Evolving Solution is reviewed always with business representative presence (Business Visionary (BV)) | 2
88 | Comments from reviews being incorporated into the Evolving Solution or team working practices | 2
89 | Reviews are recorded | 2
90 | Deliverables are accepted | 2
section score |  | 8 | 40%
Technical
91 | The development environment is appropriate for DSDM | 1
92 | The techical infrastructure is in place and/or familar to the SDT(s) | 2
93 | Technical standards are defined understood, agreed, accepted and followed by SDT(s) | 3
94 | Team Leader (TL) have clear guidance on how to implement technical standards from Technical Coordinator (TC) | 0
95 | Technical acrchitecture is clearly defined and communicated to all project members (including geographically dispersed and outsourced teams) | 1
section score |  | 7 | 28%
Lifecycle
96 | Project lifecycle is being followed | 2
97 | Lifecycle has beed tailored | 2
98 | The Project Approach Questionnaire (PAQ) is used effectively | 2
99 | The Project Approach Questionnaire (PAQ) template is updated since last use to incorporate lessons learnt | 2
section score |  | 8 | 40%
Project management
100 | The project management style is appropriate to DSDM | 2
101 | Project's governing body is working effectively | 2
section score |  | 4 | 40%
Planning and estimation
102 | DSDM planning deliverables are produced, communicated, accepted and followed (Delivery Plan, Timebox Plans) | 1
103 | SDT(s) track their work progress | 5
104 | SDT(s) estimate their work | 2
105 | Timebox estimation work and is used as a basis for project planning | 1
106 | Timebox estimation is done by SDT(s) with the business representatves (BV, BAMB) | 5
107 | Estimates are realistic | 2
108 | Estimates are done using common approach (e.g. planning poker) | 3
109 | SDT(s) velocity is tracked and used for further estimation | 3
110 | SDT(s) velocity for incoming Timebox is decreased by taking into account non-development activities (Timebox events, non-project activities, etc.) | 4
111 | Project resourced as planned | 2
112 | There are few on none changes occurring in terms of project resourcing during Timeboxes | 2
section score |  | 30 | 54.55%
Change management
113 | There is a change control process which is communicated, accepted and followed | 4
114 | Change control process is not too bureaucratic | 3
115 | Changes in project scope are clearly communicated, accepted and documented for further review | 2
116 | Reprioritisations are fed into the change control processes | 3
section score |  | 12 | 60%
Configuration management
117 | There a configuration management process which is communicated, accepted and followed | 2
118 | Evolving Solution is divided on components with dedicated owner / lead architect | 2
119 | There is a clear and followed versioning scheme | 2
120 | Evolving products are regularly baselined | 2
121 | Backtracking (tracing) is done where necessary | 2
section score |  | 10 | 40%
Risk and issues
122 | Risks and issues specific to DSDM have been identified and constantly monitored | 1
123 | Risk is being managed proactively through Timeboxes | 2
124 | Risk topic is raised (identified and communicated) during Kick-Off meetings | 3
125 | Risks are managed effectively | 4
126 | Issues are managed effectively | 5
127 | Project shopstoppers (blockers) are managed and communicated proactivelly (e.g. not during current Timebox but much earlier if possbile) | 6
128 | Scope of each Timebox is not fixed to 100% | 7
section score |  | 28 | 80%
Testing
129 | There is a valid, communicated, accepted and followed Testing Strategy | 1
130 | Testing Strategy is under governance of Technical Coordinator (TC) | 2
131 | Each SDT has at least one Solution Tester (ST) | 2
132 | Solution Tester (ST) conducts solution tests during Timebox (constantly, not just at the end of the Timebox or Increment) | 3
133 | Testing involves risk based testing approach | 2
134 | Testing involves prioritised testing based on MoSCoW prioritisation | 4
135 | Testing involves also Business Ambassador (BAMB) | 2
136 | Testing involves also UX and UI tests (if appropriate) | 2
137 | Testing is done in pairs (one person's work is tested by another person) | 2
138 | DSDM concepts for testing are applied | 4
section score |  | 24 | 48%
End of increment
139 | All requirements ommited in the increment are identified, communicated and accepted by all parties | 3
140 | Existing technical dept identified, communicated and accepted by all parties | 2
141 | Existing UX dept identified, communicated and accepted by all parties | 2
142 | There is sufficiant information to decide to proceed with further development | 3
143 | All lessons learned are documented (in a form that allows experience sharing with other teams) | 3
144 | Selected lessons learned are communicated and understood by involved parties and stakeholders | 5
section score |  | 18 | 60%
Deployment
145 | Each new Deployment delivers next set of fully developed, tested, reviewed and accepted (by the client) features | 1
146 | Communication between SDT(s) and deployment team is effective | 1
147 | SDT(s) understands well requirements and constraints involved with infrastructure | 3
section score |  | 5 | 33.33%
total score |  | 394 | 51.73%
Radar Chart Data
Business sponsorship and expectations |  | 51.43%
Business involvement |  | 40%
Roles and responsibilities |  | 84%
Empowerment |  | 84%
Team structure |  | 62%
Team dynamics |  | 88.89%
Training |  | 40%
Facilitated Workshops |  | 40%
Prioritisation |  | 30%
Timeboxing |  | 53.33%
Iterative development |  | 44%
Incremental delivery |  | 46.67%
Products |  | 53.33%
Reviews |  | 40%
Technical |  | 28%
Lifecycle |  | 40%
Project management |  | 40%
Planning and estimation |  | 54.55%
Change management |  | 60%
Configuration management |  | 40%
Risk and issues |  | 80%
Testing |  | 48%
End of increment |  | 60%
Deployment |  | 33.33%
mindmeister.com/401654536
miroslawdabrowski.com

## AgilePM V2 - RCR
AgilePM V2 Project Health Check Questionnaire (PHCQ) Radar Chart Report (RCR)
Project | Test Project ACME | Author | Mirosław Dąbrowski
Date | 2015-05-01 | Position | Agile/DSDM Coach